## Sprint1.2
Meeting Details
Report # | 2
Sprint # | 1
Date | 31.10.26
Time | 18:30
Meeting Location | Online Discord
Scrum Master Name | Martin Shihata
Product Manager Name | Youssef Habashy
Attendees
Team Member ID | Team Member Name | Github names
22001279 | Malak Makar | Malak02082005
19002212 | Youssef Abdelbary | Youssef-Abdelbary
22001226 | Ziad Agami | Ziad-Bakry
19002198 | Yara Gehad | yaragehad
19002039 | Ahmed Hazem | AhmedHazem5
19002030 | Abd El-Rahman Gamal | agragab
22002132 | Daniel Jospeh | danielljoseph
19002208 | Youssef Habashy | MintyGreen05
19002196 | Sherif Bassem | Shiko2007
19002227 | Martin Awad | Martin-Louis-Git
Absent Team Members
Team Member ID | Team Member Name | Reason for Absence

## Jira
Issue Type | Issue key | Summary | Assignee | Priority | Status
EPICS
Epic | SCRUM-204 | E1 Foundation & Shared Platform | Martin Awad | Highest | Done
Epic | SCRUM-205 | E2 Accounts & Authentication | Martin Awad, Daniel Jospeh | Highest | Done
Epic | SCRUM-206 | E3 Lender Verification | Malak Ramez | Highest | Done
Epic | SCRUM-207 | E4 Item Listings | Abd el-Rahman Gamal | Highest | Done
Epic | SCRUM-208 | E5 Catalog & Discovery | Youssef Abdelbary | Highest | Done
Epic | SCRUM-209 | E6 Wallet & Favorites | youssefhabashy.work | Medium | Done
Epic | SCRUM-210 | E7 Household Links | Yara Gehad | Medium | Done
Epic | SCRUM-211 | E8 Admin Account & Listing Management | Ahmed Hazem | Medium | Done
Epic | SCRUM-212 | E9 Platform Settings & Notices | Ziad Agami | Low | Done
TASKS/REQUIREMENTS
Task | SCRUM-213 | F1 Set up repository, environments and CI pipeline | Sherif Fawzy | Highest | Done
Task | SCRUM-214 | F2 Set up database, migrations and the users and sessions tables | Sherif Fawzy | Highest | Done
Task | SCRUM-215 | F3 Define API conventions (base path /api/v1, error format, validation, paging) | Martin Awad | Highest | Done
Task | SCRUM-224 | F4 Create catalog tables (categories, items, item_photos) | Sherif Fawzy | Highest | Done
Task | SCRUM-219 | F5 Middleware, Build role guards for guest, member, verified lender and admin (pages and API) | Yara Gehad | Highest | Done
Story | SCRUM-217 | S1 Guest: register as a member using username, name, email, password, phone number, and home address | Martin Awad | Highest | Done
Story | SCRUM-222 | S10 Member/Admin: change my password | dandanjo2016 | High | Done
Story | SCRUM-223 | S11 Member/Admin: reset a forgotten password through an OTP sent to my email | Martin Awad | High | Done
Story | SCRUM-221 | S12 Member: edit/update my profile details (phone number, address) | dandanjo2016 | High | Done
Story | SCRUM-229 | S13 Verified Lender: add an item listing with title, category, description, photos, condition notes, and deposit amount | Abd el-Rahman Gamal | Highest | Done
Story | SCRUM-230 | S14 Verified Lender: edit an item's details, deposit amount, or category | Abd el-Rahman Gamal | High | Done
Story | SCRUM-237 | S15 Verified Lender: archive/unarchive one of my item listings | Abd el-Rahman Gamal | High | Done
Story | SCRUM-235 | S16 Member: view a list of all available items including photos, category, and deposit amount | Youssef Abdelbary | Highest | Done
Story | SCRUM-238 | S17 Member: search for an item by name | Youssef Abdelbary | High | Done
Story | SCRUM-239 | S18 Member: filter items by category | Youssef Abdelbary | High | Done
Story | SCRUM-241 | S19 Member: select an item from the search/filter results | Youssef Abdelbary | High | Done
Story | SCRUM-226 | S2 Guest/Member: submit a request to become a verified lender using ID document and proof of address | Malak Ramez | Highest | Done
Story | SCRUM-236 | S20 Member: view all details of a selected item including condition notes, deposit amount, and the owner's name | Youssef Abdelbary | Highest | Done
Story | SCRUM-231 | S21 Verified Lender: view a list of all items I have listed | Abd el-Rahman Gamal | High | Done
Story | SCRUM-248 | S22 Admin: view a lender's or member's basic information | Ahmed Hazem | Medium | Done
Story | SCRUM-252 | S23 Admin: view a list of all item listings on the platform | Ahmed Hazem | Medium | Done
Story | SCRUM-254 | S24 Member: send a household-link request to another member's existing account using their email or phone number, stating our relation | Yara Gehad | Medium | Done
Story | SCRUM-255 | S25 Member: accept or decline an incoming household-link request | Yara Gehad | Medium | Done
Story | SCRUM-256 | S26 Member: view my linked household members and the status of each link (pending/accepted) | Yara Gehad | Medium | Done
Story | SCRUM-257 | S27 Member: remove a household link, unlinking that member's account from mine | Yara Gehad | Medium | Done
Story | SCRUM-247 | S28 Admin: search for a member or lender by name | Ahmed Hazem | Medium | Done
Story | SCRUM-246 | S29 Admin: view a list of all registered members and their verification status | Ahmed Hazem | Medium | Done
Story | SCRUM-225 | S3 Member: upload/remove documents (PDF, JPEG, JPG, PNG) required for my verified-lender application | Malak Ramez | Highest | Done
Story | SCRUM-232 | S30 Verified Lender: specify a pickup location and pickup instructions for an item | Abd el-Rahman Gamal | Medium | Done
Story | SCRUM-233 | S31 Verified Lender: set item-specific borrowing rules such as maximum borrow duration or a minimum trust score required to reserve it | Abd el-Rahman Gamal | Medium | Done
Story | SCRUM-234 | S32 Verified Lender: upload a usage manual/instructions document for an item | Abd el-Rahman Gamal | Medium | Done
Story | SCRUM-243 | S33 Member: view an item's usage manual before reserving it | Youssef Abdelbary | Medium | Done
Story | SCRUM-240 | S34 Member: browse items by category from a dedicated category page | Youssef Abdelbary | Medium | Done
Story | SCRUM-242 | S35 Guest: browse the public item catalog without logging in | Youssef Abdelbary | High | Done
Story | SCRUM-253 | S36 Member: view the amount in my wallet | youssefhabashy.work | Medium | Done
Story | SCRUM-244 | S37 Member: add an item to my favorites/wishlist | youssefhabashy.work | Medium | Done
Story | SCRUM-245 | S38 Member: view and remove items from my favorites list | youssefhabashy.work | Medium | Done
Story | SCRUM-250 | S39 Admin: suspend or reinstate a member's or lender's account | Ahmed Hazem | Medium | Done
Story | SCRUM-218 | S4 Member/Admin: login with username and password | Martin Awad | Highest | Done
Story | SCRUM-258 | S40 Admin: configure a deposit multiplier for high-value item categories (e.g. power tools) | Ziad Agami | Low | Done
Story | SCRUM-259 | S41 Admin: post a community notice/announcement visible to all members | Ziad Agami | Low | Done
Story | SCRUM-260 | S42 Member: view the community notice board | Ziad Agami | Low | Done
Story | SCRUM-220 | S5 Member/Admin: logout | Martin Awad | High | Done
Story | SCRUM-251 | S6 Admin: add another admin with a set username and password | Ahmed Hazem | Medium | Done
Story | SCRUM-249 | S7 Admin: remove a member/lender/admin from the system | Ahmed Hazem | Medium | Done
Story | SCRUM-227 | S8 Admin: view all documents submitted by a member applying to become a verified lender | Malak Ramez | Highest | Done
Story | SCRUM-228 | S9 Admin: accept or reject a member's request to become a verified lender | Malak Ramez | Highest | Done
|  | Front-End for Submission | Sherif Bassem | Highest | Done